## Instructions
Student Workbook Instructions	stuwbk / 20040615.v5

The student workbook provides automated support for the Personal Software Process course. The workbook includes worksheets for the calculation-intensive forms and analysis charts and tables required for reports R3, R4, and R5.

The workbook includes:
Student - a worksheet for the student background survey
Summary - a worksheet containing PSP Project Plan Summary forms for each assignment, 1A to 8A
SizeEstimate - a worksheet contining a PSP Size Estimating Template for each assignment 3A to 8A
PROBE - a worksheet that automates the PROBE method computations
TimeLog - a worksheet for recording all time log data
DefectLog - a worksheet for recording all defect data
R3 - a worksheet that generates the defect analysis tables for the R3 report
R4 - a worksheet that generates the defect analysis tables for the R4 and R5 report
Pareto - a worksheet that generates pareto distributions of defects by type and by fix time
Defect, Plan, Process, and Quality analysis worksheets that include analyses required for the R4 and R5 reports

General Instructions

1. During the planning phase of an assignment, select the assignment number using the project selector on the Summary worksheet. Calculate and enter data in all the highlighted cells containing ????? in the Plan column of the Summary worksheet for that assignment.

For assignments 3A through 8A the SizeEstimate worksheet and the PROBE worksheet are used to generate size and time estimates. The SizeEstimate worksheet replaces the PSP Size Estimating worksheet. The planned and actual LOC are entered on this form (e.g. Base LOC, Deleted LOC, Modified LOC, Base Additions, New Object LOC, and Reused LOC).

The PROBE worksheet is used to select the estimating method, regression parameters, prediction intervals, and size and time estimates. The estimate is then transferred to the SizeEstimate worksheet.

2. During the development phases, use the time and defect logs to capture actual time and defect data for the assignment, or record this data on paper forms and enter during postmortem.

3. During the postmortem phase of an assignment, calculate and enter data in all the highlighted cells that contain ????? in the Actual, ToDate, or ToDate% columns for the assignment. For assignments 3A to 8A, measure and enter actual LOC on the SizeEstimate worksheet.

4. To print a Summary report, select the assignment with the project selector and print. For assignments 1A to 6A, an extra blank page will be printed. Print page 1 only to avoid printing the blank page.

Application Notes:
A. Only enter data in highlighted fields containing ?????.
B. All other fields contain formulas that are calculated by Excel and are locked to prevent accidental entry.
C. If you need to modify a protected cell you may turn cell protection off.
D. After your modifications are complete turn cell protection back.
E. Excel will request a password when you turn protection on. DO NOT ENTER A PASSWORD.
F.The Summary worksheet automates many of the PSP calculations, but as new PSP measures appear on the worksheet, they must be calculated and entered manually.

## Student
PSP Student Background Survey
		Student Name		Student #

		Instructor Name(s)

1.0		Which of the following best describes your employment status in the software industry (mark one with an X)					Job Position

		Executive
		Management
		Senior technical
		Technical
		Full-time support
		Other

2.0		What is your software experience in: (Please specify for each category, rounded to the nearest year)					Prog. Experience
	YRS.
		In your present organization?
		In your present position?
		Your overall software experience?
		Software requirements?
		Software design?
		Code and unit test?
		Test and integration?
		Software quality assurance?
		Configuration management?
		Software process improvement/quality management?

3.0		About how much of your work-related time have you spent over the past year on each of the following? Please specify an approximate percentage for each, rounded up to the nearest whole number (with no % sign). The categories overlap, so your estimates need not total 100%					% S/W Time

		Software requirements?
		Software design?
		Code and unit test?
		Test and integration?
		Software quality assurance?
		Configuration management?
		Software process improvement/quality management?
		Other

4.0		What programming languages have you used? (Please mark as many as apply with an X)

		Ada
		Basic
		C
		C++
		Java
		PASCAL
		OBJECT PASCAL
		Visual Basic
		Visual C++
		OTHER

4.1		How many high level languages do you know well? (Please specify)					Lang#

		Number of languages

5.0		What language will you use in this course?					Language

		Ada
		Basic
		C
		C++
		Java
		PASCAL
		OBJECT PASCAL
		Visual Basic
		Visual C++
		OTHER

5.1		Approximately how much code have you written in this language? (please specify, rounded to the nearest 1,000 lines of code, e.g. 10K)					KLOC - L

		Lines of Code

5.2		Approximately how much code have you written in all languages? (please specify, rounded to the nearest 1,000 lines of code, e.g. 10K)					KLOC - T

		Lines of Code

5.3		Approximately how much code have you written in the last year? (please specify, rounded to the nearest 1,000 lines of code, e.g. 10K)					KLOC - Y

		Lines of Code - In the language you will be using
		Lines of Code - In all languages

6.0		What is the highest degree that you have attained? (please specify)

		Highest degree					Highest Degree

6.1		What was your major field of study? (please specify)

6.2		Have you had courses in any of the following subjects? (Please mark all that apply with an X)

		Statistics					Statistics
		Physical Sciences					PhyScy
		Software Project Management					ProjMgt
		Formal Software Methods					FormMeth
					YrsProg

## Summary
Project					A copy of the data entered in your StuN file.					Source: plan summary cells
1		PSP0 Project Plan Summary - Program 1A					PSP0.1 Project Plan Summary - Program 2A					PSP1 Project Plan Summary - Program 3A					PSP1.1 Project Plan Summary - Program 4A					PSP2 Project Plan Summary - Program 5A					PSP2.1 Project Plan Summary - Program 6A					PSP2.1 Project Plan Summary - Program 7A					PSP2.1 Project Plan Summary - Program 8A					PSP2.1 Project Plan Summary - Program 9A					PSP3 Project Plan Summary - Program 10A					EstObjLOC	ActObjLOC	Item:	EstLoc	ActLOC	EstMin	ActMin	EstDef	ActDef	Time by Phase					Defects Injected by Phase					Defects Removed by Phase
				Planning		Design		DLDR		Code		CR		Compile		Test		PM		Plng		Design		DLDR		Code		CR		Compile		Test		Plng		Design		DLDR		Code		CR		Compile		Test
		Student					Date		?????				Student					Date		?????				Student					Date		?????				Student					Date		?????				Student					Date		?????				Student					Date		?????				Student					Date		?????				Student					Date		?????				Student					Date		?????				Student					Date		?????					Est	Act	Est	Act	Est	Act	Est	Act	Est	Act	Est	Act	Est	Act	Est	Act	Est	Act	Est	Act	Est	Act	Est	Act	Est	Act	Est	Act	Est	Act	Est	Act	Est	Act	Est	Act	Est	Act	Est	Act	Est	Act	Est	Act
		Program	Correlation					Program#		1A				Program	LOC Counter					Program#		2A				Program	Linear Regression					Program#		3A				Program	Numerical Integration					Program#		4A				Program	Sort					Program#		5A				Program	Prediction Interval					Program#		6A				Program	Chi-square Test					Program#		7A				Program	Multiple Regression					Program#		8A				Program	Chi-square Test					Program#		9A				Program	Multiple Regression					Program#		10A					Formulas
		Instructor					Language		?????				Instructor					Language		?????				Instructor					Language		?????				Instructor					Language		?????				Instructor					Language		?????				Instructor					Language		?????				Instructor					Language		?????				Instructor					Language		?????				Instructor					Language		?????				Instructor					Language		?????					1		0	0	0		0		0		0				0				0		0		0		0		0				0				0		0		0		0				0				0		0
				2	0	0	0	0		0	0	0	0	0			0	0			0	0	0	0	0	0		0		0				0				0		0		0		0				0				0		0
				Plan		Actual		To Date		To Date%					Plan		Actual		To Date		To Date%					Plan		Actual		To Date		To Date%					Plan		Actual		To Date		To Date%					Plan		Actual		To Date		To Date%					Plan		Actual		To Date		To Date%					Plan		Actual		To Date		To Date%					Plan		Actual		To Date		To Date%					Plan		Actual		To Date		To Date%					Plan		Actual		To Date		To Date%					0	0	3	0	0	0	0		0	0	0	0	0			0	0			0	0	0	0	0	0		0		0				0				0		0		0		0				0				0		0
		Time in Phase (min.)					Program Size (LOC)					Summary					Summary					Summary					Summary					Summary					Summary					Summary					Summary					0	0	4	0	0	0	0		0	0	0	0	0			0	0			0	0	0	0	0	0		0		0				0				0		0		0		0				0				0		0
		Planning				0		0		0.0				Base(B)				?????					LOC/Hour		?????		?????		?????					LOC/Hour		0.0		0.0		0.0					LOC/Hour		0.0		0.0		0.0					LOC/Hour		0.0		0.0		0.0					LOC/Hour		0.0		0.0		0.0					LOC/Hour		0.0		0.0		0.0					LOC/Hour		0.00		0.00		0.00					LOC/Hour		0.00		0.00		0.00					0	0	5	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
		Design				0		0		0.0				Deleted(D)				?????					Planned Time		0				?????					Planned Time		0				0					Planned Time		0				0					Planned Time		0				0					Planned Time		0				0					Planned Time		0				0					Planned Time		0				0					0	0	6	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0.0	0	0.0	0	0.0	0	0.0	0	0.0	0	0.0	0	0.0	0	0.0	0	0.0	0	0.0	0	0.0	0	0.0	0	0.0	0	0.0	0
		Code				0		0		0.0				Modified(M)				?????					Program Size (LOC)					Actual Time				0		?????					Actual Time				0		0					Actual Time				0		0					Actual Time				0		0					Actual Time				0		0					Actual Time				0		0					Actual Time				0		0					0	0	7	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
		Compile				0		0		0.0				Added(A)				?????					Base(B)		0		0					CPI (Planned/Actual Time)					?????					CPI (Planned/Actual Time)					0.00					CPI (Planned/Actual Time)					0.00					CPI (Planned/Actual Time)					0.00					CPI (Planned/Actual Time)					0.00					CPI (Planned/Actual Time)					0.00					CPI (Planned/Actual Time)					0.00					0	0	8	0	0	0	0	0.0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0.0	0	0.0	0	0.0	0	0.0	0	0.0	0	0.0	0	0.0	0	0.0	0	0.0	0	0.0	0	0.0	0	0.0	0	0.0	0	0.0	0
		Test				0		0		0.0				Reused(R)				?????		?????					Deleted(D)		0		0					% Reused		?????		?????		?????					% Reused		0.0		0.0		0.0					% Reused		0.0		0.0		0.0					% Reused		0.0		0.0		0.0					% Reused		0.0		0.0		0.0					% Reused		0.0		0.0		0.0					% Reused		0.0		0.0		0.0					0	0	9	0	0	0	0	0.0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0.0	0	0.0	0	0.0	0	0.0	0	0.0	0	0.0	0	0.0	0	0.0	0	0.0	0	0.0	0	0.0	0	0.0	0	0.0	0	0.0	0
		Postmortem				0		0		0.0				Total N&C (N)		?????		?????		?????					Modified(M)		0		0					% New Reused		?????		?????		?????					% New Reused		0.0		0.0		0.0					% New Reused		0.0		0.0		0.0					% New Reused		0.0		0.0		0.0					% New Reused		0.0		0.0		0.0					% New Reused		0.0		0.0		0.0					% New Reused		0.0		0.0		0.0					0	0	10	0	0	0	0	0.0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0.0	0	0.0	0	0.0	0	0.0	0	0.0	0	0.0	0	0.0	0	0.0	0	0.0	0	0.0	0	0.0	0	0.0	0	0.0	0	0.0	0
		Total		?????		0		0	0	0.0				Total LOC(T)				?????		?????					Added(A)		0		0					Test Defects/KLOC		?????		?????		?????					Test Defects/KLOC		0.00		0.00		0.00					Test Defects/KLOC		0.00		0.00		0.00					Test Defects/KLOC		0.00		0.00		0.00					Test Defects/KLOC		0.00		0.00		0.00					Test Defects/KLOC		0.00		0.00		0.00					0	0	Totals	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
				Total New Reused				?????		?????					Reused(R)		0		0		0					Program Size (LOC)					Total Defects/KLOC		?????		?????		?????					Total Defects/KLOC		0.00		0.00		0.00					Total Defects/KLOC		0.00		0.00		0.00					Total Defects/KLOC		0.00		0.00		0.00					Total Defects/KLOC		0.00		0.00		0.00					Total Defects/KLOC		0.00		0.00		0.00
		Defects Injected					Total N&C (N)		0		0		0					Base(B)		0		0					Yield %		?????		?????		?????					Yield %		100.0		100.0		100.0					Yield %		100.0		100.0		100.0					Yield %		100.0		100.0		100.0					Yield %		100.0		100.0		100.0					Yield %		100.0		100.0		100.0
		Planning				0		0		0.0				Time in Phase (min.)					Total LOC(T)		0		?????		0					Deleted(D)		0		0					% Appraisal COQ		?????		?????		?????					% Appraisal COQ		0.0		0.0		0.0					% Appraisal COQ		0.0		0.0		0.0					% Appraisal COQ		0.0		0.0		0.0					% Appraisal COQ		0.0		0.0		0.0
		Design				0		0		0.0				Planning		?????		0		0		0.0				Total New Reused		0		0		0					Modified(M)		0		0					Program Size (LOC)					% Failure COQ		?????		?????		?????					% Failure COQ		0.0		0.0		0.0					% Failure COQ		0.0		0.0		0.0					% Failure COQ		0.0		0.0		0.0					% Failure COQ		0.0		0.0		0.0
		Code				0		0		0.0				Design		?????		0		0		0.0				Total Object LOC(E)		0		0		0					Added(A)		0		0					Base(B)		0		0					COQ A/F Ratio		?????		?????		?????					COQ A/F Ratio		0.00		0.00		0.00					COQ A/F Ratio		0.00		0.00		0.00					COQ A/F Ratio		0.00		0.00		0.00					COQ A/F Ratio		0.00		0.00		0.00
		Compile				0		0		0.0				Code		?????		0		0		0.0					Reused(R)		0		0		0					Deleted(D)		0		0
		Test				0		0		0.0				Compile		?????		0		0		0.0				Time in Phase (min.)					Total N&C (N)		0		0		0					Modified(M)		0		0					Program Size (LOC)					Program Size (LOC)					Program Size (LOC)					Program Size (LOC)					Program Size (LOC)
		Total Development				0		0	0	0.0				Test		?????		0		0		0.0				Planning		0		0		0		0.0				Total LOC(T)		0		?????		0					Added(A)		0		0					Base(B)		0		0					Base(B)		0		0					Base(B)		0		0					Base(B)		0		0					Base(B)		0		0
				Postmortem		?????		0		0		0.0				Design		0		0		0		0.0				Total New Reused		0		0		0					Reused(R)		0		0		0					Deleted(D)		0		0					Deleted(D)		0		0					Deleted(D)		0		0					Deleted(D)		0		0					Deleted(D)		0		0
		Defects Removed					Total		?????		0		0		0.0				Code		0		0		0		0.0				Total Object LOC(E)		0		0		0					Total N&C (N)		0		0		0					Modified(M)		0		0					Modified(M)		0		0					Modified(M)		0		0					Modified(M)		0		0					Modified(M)		0		0
		Planning				0		0		0.0					Compile		0		0		0		0.0					Total LOC(T)		0		?????		0					Added(A)		0		0					Added(A)		0		0					Added(A)		0		0					Added(A)		0		0					Added(A)		0		0
		Design				0		0		0.0				Defects Injected					Test		0		0		0		0.0				Time in Phase (min.)					Total New Reused		0		0		0					Reused(R)		0		0		0					Reused(R)		0		0		0					Reused(R)		0		0		0					Reused(R)		0		0		0					Reused(R)		0		0		0
		Code				0		0		0.0				Planning				0		0		0.0				Postmortem		0		0		0		0.0				Planning		0		0		0		0.0				Total Object LOC(E)		0		0		0					Total N&C (N)		0		0		0					Total N&C (N)		0		0		0					Total N&C (N)		0		0		0					Total N&C (N)		0		0		0					Total N&C (N)		0		0		0
		Compile				0		0		0.0				Design				0		0		0.0				Total		0		0		0		0.0				Design		0		0		0		0.0				UPI (70%)					Total LOC(T)		0		?????		0					Total LOC(T)		0		?????		0					Total LOC(T)		0		?????		0					Total LOC(T)		0		?????		0					Total LOC(T)		0		?????		0
		Test				0		0		0.0				Code				0		0		0.0					Code		0		0		0		0.0				LPI (70%)					Total New Reused		0		0		0					Total New Reused		0		0		0					Total New Reused		0		0		0					Total New Reused		0		0		0					Total New Reused		0		0		0
		Total Development				0		0	0	0.0				Compile				0		0		0.0				Defects Injected					Compile		0		0		0		0.0					Total Object LOC(E)		0		0		0					Total Object LOC(E)		0		0		0					Total Object LOC(E)		0		0		0					Total Object LOC(E)		0		0		0					Total Object LOC(E)		0		0		0
		After Development				?????		?????					Test				0		0		0.0				Planning				0		0		0.0				Test		0		0		0		0.0				Time in Phase (min.)					UPI (70%)					UPI (70%)					UPI (70%)					UPI (70%)					UPI (70%)
				Total Development				0		0		0.0				Design				0		0		0.0				Postmortem		0		0		0		0.0				Planning		?????		0		0		0.0				LPI (70%)					LPI (70%)					LPI (70%)					LPI (70%)					LPI (70%)
				Code				0		0		0.0				Total		0		0		0		0.0				Design		?????		0		0		0.0
				Defects Removed					Compile				0		0		0.0					Design Review		?????		0		0		0.0				Time in Phase (min.)					Time in Phase (min.)					Time in Phase (min.)					Time in Phase (min.)					Time in Phase (min.)
				Planning				0		0		0.0				Test				0		0		0.0				Defects Injected					Code		?????		0		0		0.0				Planning		0		0		0		0.0				Planning		0		0		0		0.0				Planning		0		0		0		0.0				Planning		0		0		0		0.0				Planning		0		0		0		0.0
				Design				0		0		0.0				Total Development				0		0		0.0				Planning				0		0		0.0				Code Review		?????		0		0		0.0				Design		0		0		0		0.0				Design		0		0		0		0.0				Design		0		0		0		0.0				Design		0		0		0		0.0				High-level Design		0		0		0		0.0
				Code				0		0		0.0					Design				0		0		0.0				Compile		?????		0		0		0.0				Design Review		0		0		0		0.0				Design Review		0		0		0		0.0				Design Review		0		0		0		0.0				Design Review		0		0		0		0.0				HLDR		0		0		0		0.0
				Compile				0		0		0.0				Defects Removed					Code				0		0		0.0				Test		?????		0		0		0.0				Code		0		0		0		0.0				Code		0		0		0		0.0				Code		0		0		0		0.0				Code		0		0		0		0.0				Design		0		0		0		0.0
				Test				0		0		0.0				Planning				0		0		0.0				Compile				0		0		0.0				Postmortem		?????		0		0		0.0				Code Review		0		0		0		0.0				Code Review		0		0		0		0.0				Code Review		0		0		0		0.0				Code Review		0		0		0		0.0				Design Review		0		0		0		0.0
				Total Development				0		0		0.0				Design				0		0		0.0				Test				0		0		0.0				Total		?????		0		0		0.0				Compile		0		0		0		0.0				Compile		0		0		0		0.0				Compile		0		0		0		0.0				Compile		0		0		0		0.0				Code		0		0		0		0.0
				After Development				?????		?????					Code				0		0		0.0				Total Development				0		0		0.0				UPI (70%)		?????					Test		0		0		0		0.0				Test		0		0		0		0.0				Test		0		0		0		0.0				Test		0		0		0		0.0				Code Review		0		0		0		0.0
				Compile				0		0		0.0					LPI (70%)		?????					Postmortem		0		0		0		0.0				Postmortem		0		0		0		0.0				Postmortem		0		0		0		0.0				Postmortem		0		0		0		0.0				Compile		0		0		0		0.0
				Test				0		0		0.0				Defects Removed					Total		0		0		0		0.0				Total		0		0		0		0.0				Total		0		0		0		0.0				Total		0		0		0		0.0				Test		0		0		0		0.0
				Total Development				0		0		0.0				Planning				0		0		0.0					UPI (70%)					UPI (70%)					UPI (70%)					UPI (70%)					Postmortem		0		0		0		0.0
				After Development				?????		?????					Design				0		0		0.0					LPI (70%)					LPI (70%)					LPI (70%)					LPI (70%)					Total		0		0		0		0.0
				Code				0		0		0.0					UPI (70%)
				Compile				0		0		0.0					LPI (70%)
				Test				0		0		0.0
				Total Development				0		0		0.0
				After Development				?????		?????

				PSP2 Project Plan Summary - Program 5A (Continued)					PSP2.1 Project Plan Summary - Program 6A (Continued)					PSP2.1 Project Plan Summary - Program 7A (Continued)					PSP2.1 Project Plan Summary - Program 8A (Continued)					PSP2.1 Project Plan Summary - Program 9A (Continued)					PSP3 Project Plan Summary - Program 10A (Continued)

				Student					Date		?????				Student					Date		?????				Student					Date		?????				Student					Date		?????				Student					Date		?????				Student					Date		?????
				Program	Sort					Program#		5A				Program	Prediction Interval					Program#		6A				Program	Chi-square Test					Program#		7A				Program	List Sort					Program#		8A				Program	Chi-square Test					Program#		9A				Program	Multiple Regression					Program#		10A
				Instructor					Language		?????				Instructor					Language		?????				Instructor					Language		?????				Instructor					Language		?????				Instructor					Language		?????				Instructor					Language		?????

				Plan		Actual		To Date		To Date%					Plan		Actual		To Date		To Date%					Plan		Actual		To Date		To Date%					Plan		Actual		To Date		To Date%					Plan		Actual		To Date		To Date%					Plan		Actual		To Date		To Date%
				Defects Injected					Defects Injected					Defects Injected					Defects Injected					Defects Injected					Defects Injected
				Planning		?????		0		0		0.0				Planning		0.0		0		0		0.0				Planning		0.0		0		0		0.0				Planning		0.0		0		0		0.0				Planning		0.0		0		0		0.0				Planning		0.0		0		0		0.0
				Design		?????		0		0		0.0				Design		0.0		0		0		0.0				Design		0.0		0		0		0.0				Design		0.0		0		0		0.0				Design		0.0		0		0		0.0				High-level Design		0.0		0		0		0.0
				Design Review		?????		0		0		0.0				Design Review		0.0		0		0		0.0				Design Review		0.0		0		0		0.0				Design Review		0.0		0		0		0.0				Design Review		0.0		0		0		0.0				HLDR		0.0		0		0		0.0
				Code		?????		0		0		0.0				Code		0.0		0		0		0.0				Code		0.0		0		0		0.0				Code		0.0		0		0		0.0				Code		0.0		0		0		0.0				Design		0.0		0		0		0.0
				Code Review		?????		0		0		0.0				Code Review		0.0		0		0		0.0				Code Review		0.0		0		0		0.0				Code Review		0.0		0		0		0.0				Code Review		0.0		0		0		0.0				Design Review		0.0		0		0		0.0
				Compile		?????		0		0		0.0				Compile		0.0		0		0		0.0				Compile		0.0		0		0		0.0				Compile		0.0		0		0		0.0				Compile		0.0		0		0		0.0				Code		0.0		0		0		0.0
				Test		?????		0		0		0.0				Test		0.0		0		0		0.0				Test		0.0		0		0		0.0				Test		0.0		0		0		0.0				Test		0.0		0		0		0.0				Code Review		0.0		0		0		0.0
				Total Development		?????		0		0		0.0				Total Development		0.0		0		0		0.0				Total Development		0.0		0		0		0.0				Total Development		0.0		0		0		0.0				Total Development		0.0		0		0		0.0				Compile		0.0		0		0		0.0
				Test		0.0		0		0		0.0
				Defects Removed					Defects Removed					Defects Removed					Defects Removed					Defects Removed					Total Development		0.0		0		0		0.0
				Planning		?????		0		0		0.0				Planning		0.0		0		0		0.0				Planning		0.0		0		0		0.0				Planning		0.0		0		0		0.0				Planning		0.0		0		0		0.0
				Design		?????		0		0		0.0				Design		0.0		0		0		0.0				Design		0.0		0		0		0.0				Design		0.0		0		0		0.0				Design		0.0		0		0		0.0				Defects Removed
				Design Review		?????		0		0		0.0				Design Review		0.0		0		0		0.0				Design Review		0.0		0		0		0.0				Design Review		0.0		0		0		0.0				Design Review		0.0		0		0		0.0				Planning		0.0		0		0		0.0
				Code		?????		0		0		0.0				Code		0.0		0		0		0.0				Code		0.0		0		0		0.0				Code		0.0		0		0		0.0				Code		0.0		0		0		0.0				High-level Design		0.0		0		0		0.0
				Code Review		?????		0		0		0.0				Code Review		0.0		0		0		0.0				Code Review		0.0		0		0		0.0				Code Review		0.0		0		0		0.0				Code Review		0.0		0		0		0.0				HLDR		0.0		0		0		0.0
				Compile		?????		0		0		0.0				Compile		0.0		0		0		0.0				Compile		0.0		0		0		0.0				Compile		0.0		0		0		0.0				Compile		0.0		0		0		0.0				Design		0.0		0		0		0.0
				Test		?????		0		0		0.0				Test		0.0		0		0		0.0				Test		0.0		0		0		0.0				Test		0.0		0		0		0.0				Test		0.0		0		0		0.0				Design Review		0.0		0		0		0.0
				Total Development		?????		0		0		0.0				Total Development		0.0		0		0		0.0				Total Development		0.0		0		0		0.0				Total Development		0.0		0		0		0.0				Total Development		0.0		0		0		0.0				Code		0.0		0		0		0.0
				After Development				?????		?????					After Development				?????		?????					After Development				?????		?????					After Development				?????		?????					After Development				?????		?????					Code Review		0.0		0		0		0.0
				Compile		0.0		0		0		0.0
				Defect Removal Efficiency					Defect Removal Efficiency					Defect Removal Efficiency					Defect Removal Efficiency					Defect Removal Efficiency					Test		0.0		0		0		0.0
				Def/Hr - DLDR		?????		?????		?????					Def/Hr - DLDR		0.00		0.00		0.00					Def/Hr - DLDR		0.00		0.00		0.00					Def/Hr - DLDR		0.00		0.00		0.00					Def/Hr - DLDR		0.00		0.00		0.00					Total Development		0.0		0		0		0.0
				Def/Hr - CDR		?????		?????		?????					Def/Hr - CDR		0.00		0.00		0.00					Def/Hr - CDR		0.00		0.00		0.00					Def/Hr - CDR		0.00		0.00		0.00					Def/Hr - CDR		0.00		0.00		0.00					After Development				?????		?????
				Def/Hr - Compile		?????		?????		?????					Def/Hr - Compile		0.00		0.00		0.00					Def/Hr - Compile		0.00		0.00		0.00					Def/Hr - Compile		0.00		0.00		0.00					Def/Hr - Compile		0.00		0.00		0.00
				Def/Hr - Test		?????		?????		?????					Def/Hr - Test		0.00		0.00		0.00					Def/Hr - Test		0.00		0.00		0.00					Def/Hr - Test		0.00		0.00		0.00					Def/Hr - Test		0.00		0.00		0.00					Defect Removal Efficiency
				DRL(DLDR/UT)		?????		?????		?????					DRL(DLDR/UT)		0.00		0.00		0.00					DRL(DLDR/UT)		0.00		0.00		0.00					DRL(DLDR/UT)		0.00		0.00		0.00					DRL(DLDR/UT)		0.00		0.00		0.00					Def/Hr - HLDR		0.00		0.00		0.00
				DRL(CDR/UT)		?????		?????		?????					DRL(CDR/UT)		0.00		0.00		0.00					DRL(CDR/UT)		0.00		0.00		0.00					DRL(CDR/UT)		0.00		0.00		0.00					DRL(CDR/UT)		0.00		0.00		0.00					Def/Hr - DLDR		0.00		0.00		0.00
				DRL(Compile/UT)		?????		?????		?????					DRL(Compile/UT)		0.00		0.00		0.00					DRL(Compile/UT)		0.00		0.00		0.00					DRL(Compile/UT)		0.00		0.00		0.00					DRL(Compile/UT)		0.00		0.00		0.00					Def/Hr - CDR		0.00		0.00		0.00
				Def/Hr - Compile		0.00		0.00		0.00
				Def/Hr - Test		0.00		0.00		0.00
				DRL(HLDR/UT)		0.00		0.00		0.00
				DRL(DLDR/UT)		0.00		0.00		0.00
				DRL(CDR/UT)		0.00		0.00		0.00
				DRL(Compile/UT)		0.00		0.00		0.00

## SizeEstimate
Project
1		Size Estimating Template					Size Estimating Template					Size Estimating Template					Size Estimating Template					Size Estimating Template					Size Estimating Template					Size Estimating Template
		Student	0					Date		?????			Student	0					Date		?????			Student	0					Date		?????			Student	0					Date		?????			Student	0					Date		?????			Student	0					Date		?????			Student	0					Date		?????
		Instructor	0					Program#		3A			Instructor	0					Program#		4A			Instructor	0					Program#		5A			Instructor	0					Program#		6A			Instructor	0					Program#		7A			Instructor	0					Program#		8A			Instructor	0					Program#		10A

		BASE PROGRAM LOC					ESTIMATE		ACTUAL			BASE PROGRAM LOC					ESTIMATE		ACTUAL			BASE PROGRAM LOC					ESTIMATE		ACTUAL			BASE PROGRAM LOC					ESTIMATE		ACTUAL			BASE PROGRAM LOC					ESTIMATE		ACTUAL			BASE PROGRAM LOC					ESTIMATE		ACTUAL			BASE PROGRAM LOC					ESTIMATE		ACTUAL
		BASE SIZE (B) =>					BASE SIZE (B) =>					BASE SIZE (B) =>					BASE SIZE (B) =>					BASE SIZE (B) =>					BASE SIZE (B) =>					BASE SIZE (B) =>
		LOC DELETED (D) =>					LOC DELETED (D) =>					LOC DELETED (D) =>					LOC DELETED (D) =>					LOC DELETED (D) =>					LOC DELETED (D) =>					LOC DELETED (D) =>
		LOC MODIFIED (M) =>					LOC MODIFIED (M) =>					LOC MODIFIED (M) =>					LOC MODIFIED (M) =>					LOC MODIFIED (M) =>					LOC MODIFIED (M) =>					LOC MODIFIED (M) =>
		OBJECT LOC					OBJECT LOC					OBJECT LOC					OBJECT LOC					OBJECT LOC					OBJECT LOC					OBJECT LOC
		BASE ADDITIONS:		TYPE		METHODS		REL. SIZE		LOC		LOC			BASE ADDITIONS:		TYPE		METHODS		REL. SIZE		LOC		LOC			BASE ADDITIONS:		TYPE		METHODS		REL. SIZE		LOC		LOC			BASE ADDITIONS:		TYPE		METHODS		REL. SIZE		LOC		LOC			BASE ADDITIONS:		TYPE		METHODS		REL. SIZE		LOC		LOC			BASE ADDITIONS:		TYPE		METHODS		REL. SIZE		LOC		LOC			BASE ADDITIONS:		TYPE		METHODS		REL. SIZE		LOC		LOC
					C++ Object Size in LOC per Method
					Category	VS	S	M	L	VL
					Calc	2.34	5.13	11.25	24.66	54.04
					Data	2.6	4.79	8.84	16.31	30.09
					I/O	9.01	12.06	16.15	21.62	28.93
		(BA) subtotal from page 2					0.0		0			(BA) subtotal from page 2					0.0		0			(BA) subtotal from page 2					0.0		0			(BA) subtotal from page 2					0.0		0			(BA) subtotal from page 2					0.0		0			(BA) subtotal from page 2					0.0		0			(BA) subtotal from page 2					0.0		0			Logic	7.55	10.98	15.98	23.25	33.83
		TOTAL BASE ADDITIONS (BA)					0.0		0			TOTAL BASE ADDITIONS (BA)					0.0		0			TOTAL BASE ADDITIONS (BA)					0.0		0			TOTAL BASE ADDITIONS (BA)					0.0		0			TOTAL BASE ADDITIONS (BA)					0.0		0			TOTAL BASE ADDITIONS (BA)					0.0		0			TOTAL BASE ADDITIONS (BA)					0.0		0			Set-up	3.88	5.04	6.56	8.53	11.09
		NEW OBJECTS:		TYPE		METHODS		REL. SIZE		LOC	*	LOC	*		NEW OBJECTS:		TYPE		METHODS		REL. SIZE		LOC	*	LOC	*		NEW OBJECTS:		TYPE		METHODS		REL. SIZE		LOC	*	LOC	*		NEW OBJECTS:		TYPE		METHODS		REL. SIZE		LOC	*	LOC	*		NEW OBJECTS:		TYPE		METHODS		REL. SIZE		LOC	*	LOC	*		NEW OBJECTS:		TYPE		METHODS		REL. SIZE		LOC	*	LOC	*		NEW OBJECTS:		TYPE		METHODS		REL. SIZE		LOC	*	LOC	*		Text	3.75	8	17.07	36.41	77.66

		(NO) subtotal from page 2					0.0		0			(NO) subtotal from page 2					0.0		0			(NO) subtotal from page 2					0.0		0			(NO) subtotal from page 2					0.0		0			(NO) subtotal from page 2					0.0		0			(NO) subtotal from page 2					0.0		0			(NO) subtotal from page 2					0.0		0
		TOTAL NEW OBJECTS (NO)					0.0		0			TOTAL NEW OBJECTS (NO)					0.0		0			TOTAL NEW OBJECTS (NO)					0.0		0			TOTAL NEW OBJECTS (NO)					0.0		0			TOTAL NEW OBJECTS (NO)					0.0		0			TOTAL NEW OBJECTS (NO)					0.0		0			TOTAL NEW OBJECTS (NO)					0.0		0
		REUSED OBJECTS					LOC		LOC			REUSED OBJECTS					LOC		LOC			REUSED OBJECTS					LOC		LOC			REUSED OBJECTS					LOC		LOC			REUSED OBJECTS					LOC		LOC			REUSED OBJECTS					LOC		LOC			REUSED OBJECTS					LOC		LOC

		(R) subtotal from page 2					0.0		0			(R) subtotal from page 2					0.0		0			(R) subtotal from page 2					0.0		0			(R) subtotal from page 2					0.0		0			(R) subtotal from page 2					0.0		0			(R) subtotal from page 2					0.0		0			(R) subtotal from page 2					0.0		0
		REUSED TOTAL (R)					0.0		0			REUSED TOTAL (R)					0.0		0			REUSED TOTAL (R)					0.0		0			REUSED TOTAL (R)					0.0		0			REUSED TOTAL (R)					0.0		0			REUSED TOTAL (R)					0.0		0			REUSED TOTAL (R)					0.0		0

					Size		Time					Size		Time					Size		Time					Size		Time					Size		Time					Size		Time					Size		Time
		Estimated Object LOC:				E = BA+NO+M				0					Estimated Object LOC:				E = BA+NO+M				0					Estimated Object LOC:				E = BA+NO+M				0					Estimated Object LOC:				E = BA+NO+M				0					Estimated Object LOC:				E = BA+NO+M				0					Estimated Object LOC:				E = BA+NO+M				0					Estimated Object LOC:				E = BA+NO+M				0
		Regression Parameter:				B0				0.00		0.00			Regression Parameter:				B0				0.00		0.00			Regression Parameter:				B0				0.00		0.00			Regression Parameter:				B0				0.00		0.00			Regression Parameter:				B0				0.00		0.00			Regression Parameter:				B0				0.00		0.00			Regression Parameter:				B0				0.00		0.00
		Regression Parameter:				B1				0.00		0.00			Regression Parameter:				B1				0.00		0.00			Regression Parameter:				B1				0.00		0.00			Regression Parameter:				B1				0.00		0.00			Regression Parameter:				B1				0.00		0.00			Regression Parameter:				B1				0.00		0.00			Regression Parameter:				B1				0.00		0.00
		Estimated New and Changed LOC:				N = B0 + B1` * E				0.0					Estimated New and Changed LOC:				N = B0 + B1` * E				0.0					Estimated New and Changed LOC:				N = B0 + B1` * E				0.0					Estimated New and Changed LOC:				N = B0 + B1` * E				0.0					Estimated New and Changed LOC:				N = B0 + B1` * E				0.0					Estimated New and Changed LOC:				N = B0 + B1` * E				0.0					Estimated New and Changed LOC:				N = B0 + B1` * E				0.0
		Estimated Total LOC:				T = N + B - D - M + R				0.0					Estimated Total LOC:				T = N + B - D - M + R				0.0					Estimated Total LOC:				T = N + B - D - M + R				0.0					Estimated Total LOC:				T = N + B - D - M + R				0.0					Estimated Total LOC:				T = N + B - D - M + R				0.0					Estimated Total LOC:				T = N + B - D - M + R				0.0					Estimated Total LOC:				T = N + B - D - M + R				0.0
		Estimated Total New Reuse (sum of * LOC):					0					Estimated Total New Reuse (sum of * LOC):					0					Estimated Total New Reuse (sum of * LOC):					0					Estimated Total New Reuse (sum of * LOC):					0					Estimated Total New Reuse (sum of * LOC):					0					Estimated Total New Reuse (sum of * LOC):					0					Estimated Total New Reuse (sum of * LOC):					0
		Estimated Total Developent Time:				Time = B0 + B1` * E					0.0			Estimated Total Developent Time:				Time = B0 + B1` * E					0.0			Estimated Total Developent Time:				Time = B0 + B1` * E					0.0			Estimated Total Developent Time:				Time = B0 + B1` * E					0.0			Estimated Total Developent Time:				Time = B0 + B1` * E					0.0			Estimated Total Developent Time:				Time = B0 + B1` * E					0.0			Estimated Total Developent Time:				Time = B0 + B1` * E					0.0
		Prediction Range:				Range				0.0		0.0			Prediction Range:				Range				0.0		0.0			Prediction Range:				Range				0.0		0.0			Prediction Range:				Range				0.0		0.0			Prediction Range:				Range				0.0		0.0			Prediction Range:				Range				0.0		0.0			Prediction Range:				Range				0.0		0.0
		Upper Prediction Interval:				UPI = N + Range					Upper Prediction Interval:				UPI = N + Range					Upper Prediction Interval:				UPI = N + Range					Upper Prediction Interval:				UPI = N + Range					Upper Prediction Interval:				UPI = N + Range					Upper Prediction Interval:				UPI = N + Range					Upper Prediction Interval:				UPI = N + Range
		Lower Prediction Interval:				LPI = N - Range					Lower Prediction Interval:				LPI = N - Range					Lower Prediction Interval:				LPI = N - Range					Lower Prediction Interval:				LPI = N - Range					Lower Prediction Interval:				LPI = N - Range					Lower Prediction Interval:				LPI = N - Range					Lower Prediction Interval:				LPI = N - Range
		Prediction Interval Percent					70%		70%			Prediction Interval Percent					70%		70%			Prediction Interval Percent					70%		70%			Prediction Interval Percent					70%		70%			Prediction Interval Percent					70%		70%			Prediction Interval Percent					70%		70%			Prediction Interval Percent					70%		70%
		Method Selected					0		0			Method Selected					0		0			Method Selected					0		0			Method Selected					0		0			Method Selected					0		0			Method Selected					0		0			Method Selected					0		0
		R^2					0.00		0.00			R^2					0.00		0.00			R^2					0.00		0.00			R^2					0.00		0.00			R^2					0.00		0.00			R^2					0.00		0.00			R^2					0.00		0.00

		Size Estimating Template (continued)					Size Estimating Template (continued)					Size Estimating Template (continued)					Size Estimating Template (continued)					Size Estimating Template (continued)					Size Estimating Template (continued)					Size Estimating Template (continued)
		Student	0					Date		?????			Student	0					Date		?????			Student	0					Date		?????			Student	0					Date		?????			Student	0					Date		?????			Student	0					Date		?????			Student	0					Date		?????
		Instructor	0					Program#		3A			Instructor	0					Program#		4A			Instructor	0					Program#		5A			Instructor	0					Program#		6A			Instructor	0					Program#		7A			Instructor	0					Program#		8A			Instructor	0					Program#		10A

		OBJECT LOC					ESTIMATE		ACTUAL			OBJECT LOC					ESTIMATE		ACTUAL			OBJECT LOC					ESTIMATE		ACTUAL			OBJECT LOC					ESTIMATE		ACTUAL			OBJECT LOC					ESTIMATE		ACTUAL			OBJECT LOC					ESTIMATE		ACTUAL			OBJECT LOC					ESTIMATE		ACTUAL
		BASE ADDITIONS:		TYPE		METHODS		REL. SIZE		LOC		LOC			BASE ADDITIONS:		TYPE		METHODS		REL. SIZE		LOC		LOC			BASE ADDITIONS:		TYPE		METHODS		REL. SIZE		LOC		LOC			BASE ADDITIONS:		TYPE		METHODS		REL. SIZE		LOC		LOC			BASE ADDITIONS:		TYPE		METHODS		REL. SIZE		LOC		LOC			BASE ADDITIONS:		TYPE		METHODS		REL. SIZE		LOC		LOC			BASE ADDITIONS:		TYPE		METHODS		REL. SIZE		LOC		LOC
					C++ Object Size in LOC per Method
					Category	VS	S	M	L	VL
					Calc	2.34	5.13	11.25	24.66	54.04
					Data	2.6	4.79	8.84	16.31	30.09
					I/O	9.01	12.06	16.15	21.62	28.93
					Logic	7.55	10.98	15.98	23.25	33.83
					Set-up	3.88	5.04	6.56	8.53	11.09
					Text	3.75	8	17.07	36.41	77.66

		SUBTOTAL BASE ADDITIONS (BA) =>					0.0		0			SUBTOTAL BASE ADDITIONS (BA) =>					0.0		0			SUBTOTAL BASE ADDITIONS (BA) =>					0.0		0			SUBTOTAL BASE ADDITIONS (BA) =>					0.0		0			SUBTOTAL BASE ADDITIONS (BA) =>					0.0		0			SUBTOTAL BASE ADDITIONS (BA) =>					0.0		0			SUBTOTAL BASE ADDITIONS (BA) =>					0.0		0
		NEW OBJECTS:		TYPE		METHODS		REL. SIZE		LOC	*	LOC	*		NEW OBJECTS:		TYPE		METHODS		REL. SIZE		LOC	*	LOC	*		NEW OBJECTS:		TYPE		METHODS		REL. SIZE		LOC	*	LOC	*		NEW OBJECTS:		TYPE		METHODS		REL. SIZE		LOC	*	LOC	*		NEW OBJECTS:		TYPE		METHODS		REL. SIZE		LOC	*	LOC	*		NEW OBJECTS:		TYPE		METHODS		REL. SIZE		LOC	*	LOC	*		NEW OBJECTS:		TYPE		METHODS		REL. SIZE		LOC	*	LOC	*

		SUBTOTAL NEW OBJECTS (NO) =>					0.0		0			SUBTOTAL NEW OBJECTS (NO) =>					0.0		0			SUBTOTAL NEW OBJECTS (NO) =>					0.0		0			SUBTOTAL NEW OBJECTS (NO) =>					0.0		0			SUBTOTAL NEW OBJECTS (NO) =>					0.0		0			SUBTOTAL NEW OBJECTS (NO) =>					0.0		0			SUBTOTAL NEW OBJECTS (NO) =>					0.0		0
		REUSED OBJECTS					LOC		LOC			REUSED OBJECTS					LOC		LOC			REUSED OBJECTS					LOC		LOC			REUSED OBJECTS					LOC		LOC			REUSED OBJECTS					LOC		LOC			REUSED OBJECTS					LOC		LOC			REUSED OBJECTS					LOC		LOC

		SUBTOTAL REUSED (R) =>					0.0		0			SUBTOTAL REUSED (R) =>					0.0		0			SUBTOTAL REUSED (R) =>					0.0		0			SUBTOTAL REUSED (R) =>					0.0		0			SUBTOTAL REUSED (R) =>					0.0		0			SUBTOTAL REUSED (R) =>					0.0		0			SUBTOTAL REUSED (R) =>					0.0		0

## PROBE
PROBE Method Selector			PROBE Method Calculations					Historical Data					Regression Data
Project	1		PROBE Method	A		B		C		D			Prog	Est. (N&C)	Actual (N&C)	Actual Min.	Est. (E)	Outliers		Item	Est. (E) / Xi	Act. (N) / Yi	Act. Min. / Yi	Est. (N) / Xi	Act. (N) / Yi	Act. Min. / Yi
Estimate (E)	0			Size	Time	Size	Time	Size	Time	Size	Time		1		0					1					ESTIMATION RESULTS
Size Method	4		Estimate	#VALUE!	#VALUE!	#VALUE!	#VALUE!	Err:502	Err:502	0			2	0	0					2					SIZE					TIME
Selector			R-Squared	#VALUE!	#VALUE!	#VALUE!	#VALUE!					3	0	0		0			3					M	E	R	B0	B1	R2	M	E	R	B0	B1	R2
Size Estimate	0		Beta0	#VALUE!	#VALUE!	#VALUE!	#VALUE!	0.00	0.00	0.00	0.00		4	0	0		0			4
Range	0		Beta1	#VALUE!	#VALUE!	#VALUE!	#VALUE!	Err:502	Err:502	1.00	#DIV/0!		5	0	0		0			5
B0	0		Range (70%)	#NAME?	#NAME?	#NAME?	#NAME?					6	0	0		0			6
B1	1		UPI	#VALUE!	#VALUE!	#VALUE!	#VALUE!					7	0	0		0			7
R^2	0		LPI	#VALUE!	#VALUE!	#VALUE!	#VALUE!					8	0	0		0			8
Time Method	4		Variance	#NAME?	#NAME?	#NAME?	#NAME?					9
Selector			Std. Deviation	#NAME?	#NAME?	#NAME?	#NAME?
Time Estimate	0
Range	0	Method C Est. vs. Act. Size / Est. Size / Actual Size					Method C Est. Size vs. Act. Time / Est. Size / Actual Time
B0	0
B1	#DIV/0!
R^2	0

## PROBE.XLM
Names	Formulas	Comments	Copyright 1996 James W. Over
	LRVariance	knownYs, knownXs, betaO, beta1
	#NAME?
	#NAME?
	#NAME?
	#NAME?
	#NAME?
LRVSum	0
	#NAME?
LRVy	Err:502
LRVx	Err:502
	#NAME?
	#NAME?
	#NAME?
	#NAME?

	PredictionRange	known Ys, known Xs, beta0, beta1, Xk, prcnt
	#NAME?
	#NAME?
	#NAME?	Copyright 1996 James W. Over
	#NAME?
	#NAME?
	#NAME?
	#NAME?
LRPRVar	#ADDIN?
LRPRStd	#ADDIN?
LRPRt	Err:502
LRPRXavg	#N/A
LRPRVSum	0
	#NAME?
LRPRVx	Err:502
	#NAME?
	#NAME?
	#NAME?
	#NAME?

## TimeLog
Project	Phase	Date	Start	Int.	Stop	Delta	Comments

## DefectLog
Project	Date	Num	Type	Injected	Removed	FixTime	Fix Ref.	Description

## R3
Defect Densities				Compile and Test Defects
Program Number	New and Changed LOC	Total Defects	Defects per KLOC	Defects found in compile	Compile defects per KLOC	Defects found in test	Test defects per KLOC
1	0	0	0	0	0	0	0
2	0	0	0	0	0	0	0
3	0	0	0	0	0	0	0
4	0	0	0	0	0	0	0
5	0	0	0	0	0	0	0
6	0	0	0	0	0	0	0
7	0	0	0	0	0	0	0
8	0	0	0	0	0	0	0
9	0	0	0	0	0	0	0
10	0	0	0	0	0	0	0
Totals	0	0	0	0	0	0	0

Defect Fix Times
		Defects found in compiling	Defects found in testing	Total defects found
Defects	Tot. fix time	#NAME?	#NAME?	#NAME?
injected in	Tot. defects	#NAME?	#NAME?	#NAME?
designing	Avg. fix time	#NAME?	#NAME?	#NAME?
Defects	Tot. fix time	#NAME?	#NAME?	#NAME?
injected in	Tot. defects	#NAME?	#NAME?	#NAME?
coding	Avg. fix time	#NAME?	#NAME?	#NAME?
Total	Tot. fix time	#NAME?	#NAME?	#NAME?
defects	Tot. defects	#NAME?	#NAME?	#NAME?
injected	Avg. fix time	#NAME?	#NAME?	#NAME?

Database criteria for defect fix times				Criteria for->	injected in...	found in...
Injected	Removed	fixtime	total		design	compile
DLD	COMPILE	#NAME?	#NAME?
Injected	Removed	fixtime	total		design	test
DLD	TEST	#NAME?	#NAME?
Injected		fixtime	total		design	anywhere
DLD		#NAME?	#NAME?
Injected	Removed	fixtime	total		coding	compile
CODE	COMPILE	#NAME?	#NAME?
Injected	Removed	fixtime	total		coding	test
CODE	TEST	#NAME?	#NAME?
Injected		fixtime	total		coding	anywhere
CODE		#NAME?	#NAME?
	Removed	fixtime	total		anywhere	complie
	COMPILE	#NAME?	#NAME?
	Removed	fixtime	total		anywhere	test
	TEST	#NAME?	#NAME?
		fixtime	total		anywhere	anywhere
		#NAME?	#NAME?

## R4
		Table D23

	Number Injected		Percentage Injected		Number Removed		Percentage Removed
Type	Design	Code	Design	Code	Compile	Test	Compile	Test
10	#NAME?	#NAME?	#NAME?	#NAME?	#NAME?	#NAME?	#NAME?	#NAME?
20	#NAME?	#NAME?	#NAME?	#NAME?	#NAME?	#NAME?	#NAME?	#NAME?
30	#NAME?	#NAME?	#NAME?	#NAME?	#NAME?	#NAME?	#NAME?	#NAME?
40	#NAME?	#NAME?	#NAME?	#NAME?	#NAME?	#NAME?	#NAME?	#NAME?
50	#NAME?	#NAME?	#NAME?	#NAME?	#NAME?	#NAME?	#NAME?	#NAME?
60	#NAME?	#NAME?	#NAME?	#NAME?	#NAME?	#NAME?	#NAME?	#NAME?
70	#NAME?	#NAME?	#NAME?	#NAME?	#NAME?	#NAME?	#NAME?	#NAME?
80	#NAME?	#NAME?	#NAME?	#NAME?	#NAME?	#NAME?	#NAME?	#NAME?
90	#NAME?	#NAME?	#NAME?	#NAME?	#NAME?	#NAME?	#NAME?	#NAME?
100	#NAME?	#NAME?	#NAME?	#NAME?	#NAME?	#NAME?	#NAME?	#NAME?
Total	#NAME?	#NAME?			#NAME?	#NAME?

		Table D24

Defect Type		Number of defects through Compile		Number of defects found in Compile		Percentage of Type found by the Compiler
10		#NAME?		#NAME?		#NAME?
20		#NAME?		#NAME?		#NAME?
30		#NAME?		#NAME?		#NAME?
40		#NAME?		#NAME?		#NAME?
50		#NAME?		#NAME?		#NAME?
60		#NAME?		#NAME?		#NAME?
70		#NAME?		#NAME?		#NAME?
80		#NAME?		#NAME?		#NAME?
90		#NAME?		#NAME?		#NAME?
100		#NAME?		#NAME?		#NAME?
Total		#NAME?		#NAME?		#NAME?

Injected Criteria					Removed Criteria					Injected/Removed Criteria
Injected	Type	Injected			Removed	Type	Removed			Injected	Type	Removed
DLD	10	CODE			COMPILE	10	TEST			PLAN	10	PLAN
Injected	Type	Injected			Removed	Type	Removed			DLD	10	DLD
DLD	20	CODE			COMPILE	20	TEST			DLDR	10	DLDR
Injected	Type	Injected			Removed	Type	Removed			CODE	10	CODE
DLD	30	CODE			COMPILE	30	TEST			CR	10	CR
Injected	Type	Injected			Removed	Type	Removed			COMPILE	10	COMPILE
DLD	40	CODE			COMPILE	40	TEST			Injected	Type	Removed
Injected	Type	Injected			Removed	Type	Removed			PLAN	20	PLAN
DLD	50	CODE			COMPILE	50	TEST			DLD	20	DLD
Injected	Type	Injected			Removed	Type	Removed			DLDR	20	DLDR
DLD	60	CODE			COMPILE	60	TEST			CODE	20	CODE
Injected	Type	Injected			Removed	Type	Removed			CR	20	CR
DLD	70	CODE			COMPILE	70	TEST			COMPILE	20	COMPILE
Injected	Type	Injected			Removed	Type	Removed			Injected	Type	Removed
DLD	80	CODE			COMPILE	80	TEST			PLAN	30	PLAN
Injected	Type	Injected			Removed	Type	Removed			DLD	30	DLD
DLD	90	CODE			COMPILE	90	TEST			DLDR	30	DLDR
Injected	Type	Injected			Removed	Type	Removed			CODE	30	CODE
DLD	100	CODE			COMPILE	100	TEST			CR	30	CR
							COMPILE	30	COMPILE
							Injected	Type	Removed
							PLAN	40	PLAN
							DLD	40	DLD
							DLDR	40	DLDR
							CODE	40	CODE
							CR	40	CR
							COMPILE	40	COMPILE
							Injected	Type	Removed
							PLAN	50	PLAN
							DLD	50	DLD
							DLDR	50	DLDR
							CODE	50	CODE
							CR	50	CR
							COMPILE	50	COMPILE
							Injected	Type	Removed
							PLAN	60	PLAN
							DLD	60	DLD
							DLDR	60	DLDR
							CODE	60	CODE
							CR	60	CR
							COMPILE	60	COMPILE
							Injected	Type	Removed
							PLAN	70	PLAN
							DLD	70	DLD
							DLDR	70	DLDR
							CODE	70	CODE
							CR	70	CR
							COMPILE	70	COMPILE
							Injected	Type	Removed
							PLAN	80	PLAN
							DLD	80	DLD
							DLDR	80	DLDR
							CODE	80	CODE
							CR	80	CR
							COMPILE	80	COMPILE
							Injected	Type	Removed
							PLAN	90	PLAN
							DLD	90	DLD
							DLDR	90	DLDR
							CODE	90	CODE
							CR	90	CR
							COMPILE	90	COMPILE
							Injected	Type	Removed
							PLAN	100	PLAN
							DLD	100	DLD
							DLDR	100	DLDR
							CODE	100	CODE
							CR	100	CR
							COMPILE	100	COMPILE

## Pareto
10 / Defects Removed By Type	0	10	0
20	0	20	0
30	0	30	0
40	0	40	0
50	0	50	0
60	0	60	0
70	0	70	0
80	0	80	0
90	0	90	0
100	0	100	0

Defect Fix Time By Type

## DefectAnalysis
Analysis of the defect data for the programs you have written to date.
Total defects per KLOC
Defects per KLOC injected in design and code
Defects per KLOC removed in design review, code review, compile, and test
Defect % distribution by phase, injected and removed
x-y plot of compile vs. test defects

Total Defects / Program Number / Defects/KLOC					Defects Injected in Design / Program Number / Defects/KLOC					Defects Injected in Code / Program Number / Defects/KLOC					Defects Removed in Design Review / Program Number / Defects/KLOC					Defects Removed in Code Review / Program Number / Defects/KLOC					Defects Removed in Compile / Program Number / Defects/KLOC					Defects Removed in Test / Program Number / Defects/KLOC					Defect Injection % by Phase / Program Number / %					Defect Removal % by Phase / Program Number / %					Compile vs. Test Defects / Compile Defects/KLOC / Test Defects/KLOC

A copy of selected portions of your development data, as entered in your Summary file.
Item:	EstLOC	ActLOC	EstMin	ActMin	EstDef	ActDef	Time by Phase					Defects Injected by Phase					Defects Removed by Phase
					Planning	Design	Design	Code	Code	Compile	Test	PM	Planning	Design	Design	Code	Code	Compile	Test	Planning	Design	Design	Code	Code	Compile	Test
					Review		Review					Review		Review					Review		Review
Formulas
1		0	0	0	0	0	0	0		0		0	0	0	0	0		0		0	0	0	0		0		0	0
2	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
3	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
4	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
5	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
6	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
7	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
8	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
9	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
10	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
Totals	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0

Analysis calculations
	Total Def		Def. Inj. in Design		Def. inj. in Code		Def. rem. in Des. Rev.		Def. rem. in CodeRev.		DefRemComp		DefRemTest
	Def/KLOC		Def/KLOC		Def/KLOC		Def/KLOC		Def/KLOC		Def/KLOC		Def/KLOC

Formulas	0		0		0		0		0		0		0
1	0		0		0		0		0		0		0
2	0		0		0		0		0		0		0
3	0		0		0		0		0		0		0
4	0		0		0		0		0		0		0
5	0		0		0		0		0		0		0
6	0		0		0		0		0		0		0
7	0		0		0		0		0		0		0
8	0		0		0		0		0		0		0
9	0		0		0		0		0		0		0
10	0		0		0		0		0		0		0
Totals	0		0		0		0		0		0		0

	Defect Injection Distribution - % by phase
	Plng	Des	Design	DLDR	Des.Rev	Code	Code	CDR	CDR	Comp	Comp	Test	Test
			Cum.		Cum		Cum		Cum		Cum		Cum
Formulas	0	0	0	0	0	0	0	0	0	0	0	0	0
1	0	0	0	0	0	0	0	0	0	0	0	0	0
2	0	0	0	0	0	0	0	0	0	0	0	0	0
3	0	0	0	0	0	0	0	0	0	0	0	0	0
4	0	0	0	0	0	0	0	0	0	0	0	0	0
5	0	0	0	0	0	0	0	0	0	0	0	0	0
6	0	0	0	0	0	0	0	0	0	0	0	0	0
7	0	0	0	0	0	0	0	0	0	0	0	0	0
8	0	0	0	0	0	0	0	0	0	0	0	0	0
9	0	0	0	0	0	0	0	0	0	0	0	0	0
10	0	0	0	0	0	0	0	0	0	0	0	0	0
Total	0	0	0	0	0	0	0	0	0	0	0	0	0

	Defect Removal Distribution - % by phase
	Planning	Design	Design	Des.Rev	Des.Rev	Code	Code	CDR	CDR	Comp	Comp	Test	Test
			Cum.		Cum		Cum		Cum		Cum		Cum
Formulas	0	0	0	0	0	0	0	0	0	0	0	0	0
1	0	0	0	0	0	0	0	0	0	0	0	0	0
2	0	0	0	0	0	0	0	0	0	0	0	0	0
3	0	0	0	0	0	0	0	0	0	0	0	0	0
4	0	0	0	0	0	0	0	0	0	0	0	0	0
5	0	0	0	0	0	0	0	0	0	0	0	0	0
6	0	0	0	0	0	0	0	0	0	0	0	0	0
7	0	0	0	0	0	0	0	0	0	0	0	0	0
8	0	0	0	0	0	0	0	0	0	0	0	0	0
9	0	0	0	0	0	0	0	0	0	0	0	0	0
10	0	0	0	0	0	0	0	0	0	0	0	0	0
Totals	0	0	0	0	0	0	0	0	0	0	0	0	0

## PlanAnalysis
Analysis of the time spent developing the programs to date
Size and size estimating error
Development time and time estimating error
Percent of development time spent in planning, postmortem, compile, and test

Actual Size / Program Number / LOC					Size Estimating Error / Program Number / %					Actual Development Time / Program Number / Hours					Time Estimating Error / Program Number / %					% Planning Time / Program Number / %					% Postmortem Time / Program Number / %					% Plan + Postmortem Time / Program Number / %					% Compile Time / Program Number / %					% Test Time / Program Number / %					% Compile + Test Time / Program Number / %

A copy of selected portions of your development data, as entered in your Summary file.
Item:	EstLoc	ActLoc	EstMin	ActLoc	EstDef	ActDef	Time by Phase					Defects Injected by Phase					Defects Removed by Phase
					Planning	Design	Design	Code	Code	Compile	Test	PM	Planning	Design	Design	Code	Code	Compile	Test	Planning	Design	Design	Code	Code	Compile	Test
					Review		Review					Review		Review					Review		Review
Formulas
1		0	0	0	0	0	0	0		0		0	0	0	0	0		0		0	0	0	0		0		0	0
2	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
3	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
4	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
5	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
6	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
7	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
8	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
9	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
10	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
Totals	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0

Analysis calculations
	Size Error		Time		Time Error		Plan Time		PM Time		Plan+PM Time		Compile Time		Test Time		Compile+Test Time
	%		Hours		%		%		%		%		%		%		%
Formulas	0		0		0		0		0		0		0		0		0
1	#VALUE!		0		0		0		0		0		0		0		0
2	0		0		0		0		0		0		0		0		0
3	0		0		0		0		0		0		0		0		0
4	0		0		0		0		0		0		0		0		0
5	0		0		0		0		0		0		0		0		0
6	0		0		0		0		0		0		0		0		0
7	0		0		0		0		0		0		0		0		0
8	0		0		0		0		0		0		0		0		0
9	0		0		0		0		0		0		0		0		0
10	0		0		0		0		0		0		0		0		0
Totals	#VALUE!		0		0		0		0		0		0		0		0

## ProcessAnalysis
Analysis of the quality of the process used for the programs you have written to date.
Productivity
Comparative x-y plots of productivity, yield, A/FR, and test defects

Productivity / Program Number / LOC/Hour					Productivity vs. Yield / Yield % / Productivity (LOC/Hour)					Productivity vs. A/FR / Appraisal to Failure Ratio (A/FR) / Productivity (LOC/Hour)					Yield vs. A/FR / Appraisal to Failure Ratio (A/FR) / Yield %					A/FR vs. Yield / Yield / Appraisal to Failure Ratio (A/FR)					Test Defects vs. A/FR / Appraisal to Failure Ratio (A/FR) / Defects/KLOC					Test Defects vs. Yield / Yield % / Defects/KLOC

A copy of selected portions of your development data, as entered in your Summary file.
Item:	EstLoc	ActLoc	EstMin	ActMin	EstDef	ActDef	Time by Phase					Defects Injected by Phase					Defects Removed by Phase
					Planning	Design	Design	Code	Code	Compile	Test	PM	Planning	Design	Design	Code	Code	Compile	Test	Planning	Design	Design	Code	Code	Compile	Test
					Review		Review					Review		Review					Review		Review
Formulas
1		0	0	0	0	0	0	0		0		0	0	0	0	0		0		0	0	0	0		0		0	0
2	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
3	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
4	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
5	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
6	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
7	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
8	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
9	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
10	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
Totals	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0

Analysis calculations
	Yield				Cost of Quality					DefRemTest		Productivity
	Early inj.	Early rem.	Yield%		Failure	Appraisal	TotalCOQ	A/FR		Def/KLOC		LOC/Hour
					Cost	Cost
Formulas	0	0	0		0	0	0	0		0		0
1	#VALUE!	#VALUE!	#VALUE!		0	0	0	0		0		0
2	0	0	0		0	0	0	0		0		0
3	0	0	0		0	0	0	0		0		0
4	0	0	0		0	0	0	0		0		0
5	0	0	0		0	0	0	0		0		0
6	0	0	0		0	0	0	0		0		0
7	0	0	0		0	0	0	0		0		0
8	0	0	0		0	0	0	0		0		0
9	0	0	0		0	0	0	0		0		0
10	0	0	0		0	0	0	0		0		0
Totals	#VALUE!	#VALUE!	#VALUE!		0	0	0	0		0		0

## QualityAnalysis
Analysis of the quality data for the programs you have written to date.
Yield
Cost of Quality
Appraisal to failure ratio (A/FR)
LOC reviewed per hour vs. yield

Defect Removal Yield / Program Number / Yield %					Failure Cost of Quality / Program Number / Failure Cost %					Apppraisal Cost of Quality / Program Number / Appraisal Cost %					Total Cost of Quality / Program Number / Total Cost of Quality %					Appraisal To Failure Ratio / Program Number / A/FR					LOC Reviewed per Hour / Program Number / LOC/Hour					LOC Reviewed per Hour vs. Yield - Design Review / Design Review LOC/Hour / Yield					LOC Reviewed per Hour vs. Yield - Code Review / Code Review LOC/Hour / Yield					LOC Reviewed per Hour vs. Yield - Design and Code Review / Design and Code Review LOC/Hour / Yield

A copy of selected portions of your development data, as entered in your Summary file.
Item:	EstLoc	ActLoc	EstMin	ActLoc	EstDef	ActDef	Time by Phase					Defects Injected by Phase					Defects Removed by Phase
					Planning	Design	Design	Code	Code	Compile	Test	PM	Planning	Design	Design	Code	Code	Compile	Test	Planning	Design	Design	Code	Code	Compile	Test
					Review		Review					Review		Review					Review		Review
Formulas
1		0	0	0	0	0	0	0		0		0	0	0	0	0		0		0	0	0	0		0		0	0
2	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
3	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
4	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
5	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
6	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
7	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
8	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
9	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
10	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
Totals	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0

Analysis calculations
	Yield				Cost of Quality					DefRemTest		LOC Reviewed/Hour				Review Yield
	Early inj.	Early rem.	Yield%		Failure	Appraisal	TotalCOQ	A/FR		Def/KLOC		DLDR	CDR	Both		DLDR	CDR
					Cost	Cost
Formulas	0	0	0		0	0	0	0		0		0	0	0		0	0
1	#VALUE!	#VALUE!	#VALUE!		0	0	0	0		0		#VALUE!	#VALUE!	#VALUE!		#VALUE!	#VALUE!
2	0	0	0		0	0	0	0		0		0	0	0		0	0
3	0	0	0		0	0	0	0		0		0	0	0		0	0
4	0	0	0		0	0	0	0		0		0	0	0		0	0
5	0	0	0		0	0	0	0		0		0	0	0		0	0
6	0	0	0		0	0	0	0		0		0	0	0		0	0
7	0	0	0		0	0	0	0		0		0	0	0		0	0
8	0	0	0		0	0	0	0		0		0	0	0		0	0
9	0	0	0		0	0	0	0		0		0	0	0		0	0
10	0	0	0		0	0	0	0		0		0	0	0		0	0
Totals	#VALUE!	#VALUE!	#VALUE!		0	0	0	0		0		#VALUE!	#VALUE!	#VALUE!		#VALUE!	#VALUE!

## SCMENUS
Project	Assignment	Process		Processes		Phases		PSP0		PSP0.1		PSP1		PSP1.1		PSP2		PSP2.1				Type	Description		Object Type	Object Type		Relative Size		Method
1	1A	PSP0		PSP0		PLAN		PLAN		PLAN		PLAN		PLAN		PLAN		PLAN				10	Documentation		C	Calculation		VS		A
2	2A	PSP0.1		PSP0.1		DLD		DLD		DLD		DLD		DLD		DLD		DLD				20	Syntax		D	Data		S		B
3	3A	PSP1		PSP1		DLDR		CODE		CODE		CODE		CODE		DLDR		DLDR				30	Build, Package		IO	Input/Output		M		C
4	4A	PSP1.1		PSP1.1		CODE		COMPILE		COMPILE		COMPILE		COMPILE		CODE		CODE				40	Assignment		L	Logic		L		D
5	5A	PSP2		PSP2		CR		TEST		TEST		TEST		TEST		CR		CR				50	Interface		S	Set-up		VL
6	6A	PSP2.1		PSP2.1		COMPILE		PM		PM		PM		PM		COMPILE		COMPILE				60	Checking		T	Text
7	7A	PSP2.1				TEST										TEST		TEST				70	Data
8	8A	PSP2.1				PM										PM		PM				80	Function
																						90	System
																						100	Environment

## ProjDB
Project	STU1 compatible		Time Summary		Defect Summary		Time by Phase					Defects Injected by Phase					Defects Removed by Phase					Size					Size Estimate		Time in Phase Est.
Number	Size N&C					PLAN		HLD		HLDR		DLD		DLDR		CODE		CR		COMPILE		TEST		PM		PLAN		HLD		HLDR		DLD		DLDR		CODE		CR		COMPILE		TEST		PM		PLAN		HLD		HLDR		DLD		DLDR		CODE		CR		COMPILE		TEST		PM		Base		Deleted		Modified		Added		Reused		New and Changed		Total		Total New Reuse		Object LOC		Pred. Intervals		Pred. Intervals		Project
Item:	EstLoc	ActLOC	EstMin	ActMin	EstDef	ActDef	Est	Act	Est	Act	Est	Act	Est	Act	Est	Act	Est	Act	Est	Act	Est	Act	Est	Act	Est	Act	Est	Act	Est	Act	Est	Act	Est	Act	Est	Act	Est	Act	Est	Act	Est	Act	Est	Act	Est	Act	Est	Act	Est	Act	Est	Act	Est	Act	Est	Act	Est	Act	Est	Act	Est	Act	Est	Act	Est	Act	Est	Act	Est	Act	Est	Act	Est	Act	Est	Act	Est	Act	Est	Act	Est	Act	Est	Act	UPI	LPI	UPI	LPI	Date	Language
1					0	0	0	0	0	0	0	0
2					0	0	0	0	0	0	0	0
3					0	0	0	0	0	0	0	0
4					0	0	0	0	0	0	0	0
5					0	0	0	0	0	0	0	0
6					0	0	0	0	0	0	0	0
7					0	0	0	0	0	0	0	0
8					0	0	0	0	0	0	0	0
9					0	0	0	0	0	0	0	0
10					0	0	0	0	0	0	0	0

		This worksheet holds the roll-up of actual time and defect data from the time log and defect log.

				This worksheet holds the roll-up of actual time and defect data from the time log and defect log. / Worksheet pdb uses references to this worksheet for actual time in phase, defects injected in phase, and defects removed in phase. / Worksheet Summary uses references to worksheet pdb for actual data.

## pdb
	Time in Phase					Defects Injected					Defects Removed
Program	Plan	HLD	HLDR	Design	DLDR	Code	CR	Compile	Test	PM	Plan	HLD	HLDR	Design	DLDR	Code	CR	Compile	Test	PM	Plan	HLD	HLDR	Design	DLDR	Code	CR	Compile	Test	PM
1	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0		0
2	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0		0
3	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0		0
4	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0		0
5	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0		0
6	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0		0
7	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0		0
8	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0		0
9	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0		0
10	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0		0
	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0	0
				0					0					0

		This worksheet references worksheet ProjDB to get actual time and defect data. / Worksheet Summary uses references to this worksheet for actual time in phase, defects injected in phase, and defects removed in phase.